## Sheet1
Week | Phase | Key Activities | Timeline | Output
1 | Project Initiation & Planning | Define project scope, deliverables, and risks; Identify stakeholders; System Architecture Draft | Week 1 | https://github.com/aditya0x404/AQIpredict
2 | Research & System Design | Research existing models; Create System Architecture Diagram; Define Data Flow & Tech Stack | Week 2 | https://miro.com/app/board/uXjVILVzyIg=/?share_link_id=956367454051
https://miro.com/app/board/uXjVILVx72A=/
3 | Data Collection & Preprocessing | Collect AQI/weather data; Data Cleaning & Feature Engineering; Store in DB; EDA
4 | Data Collection & Preprocessing | Collect AQI/weather data; Data Cleaning & Feature Engineering; Store in DB; EDA
5 | Model Development & Training | Train ML & DL models (LSTM, XGBoost, RF); Hyperparameter tuning; Model evaluation
6 | Model Development & Training | Train ML & DL models (LSTM, XGBoost, RF); Hyperparameter tuning; Model evaluation
7 | Backend Development & API Creation | Develop REST API (Flask/FastAPI); Implement authentication, logging; Test API
8 | Frontend Development & Dashboard | Develop Web UI (React.js/Vue.js); Integrate Maps & Charts; Real-time AQI visualization
9 | Integration, Testing & Optimization | Connect frontend with API & DB; Perform unit & API testing; Optimize performance
10 | Integration, Testing & Optimization | Connect frontend with API & DB; Perform unit & API testing; Optimize performance
11 | Final Testing, Documentation & Handover | Conduct UAT Testing; Create Documentation & User Guide; Final Deployment
12 | Documentation & Presentation | Final Presentation of the Project